# ~~Minutes~~ Minute 3/9/2010

1. **Report preparing:**
   1. Slide

* Each member prepares his related papers’ / documents’ reference and add to SVN server in his branch. Deadline: 20h – 5/9/2010
* Mr. C.Thang has responsibility ~~to~~ for ~~summary~~ summarizing and ~~number~~ numbering ~~to~~ each reference. Deadline: 23h – 5/9/2010
* Each member links his report parts to corresponding references. Deadline: 22h – 6/9/2010
* Each member must review his part in slide to report to teacher.
  1. Next approaches (ask for teacher’s opinion)
* Alert correlation
* Visualization techniques
* Components interaction formats/ protocol + language
* Plan recognition
  + Matching algorithm
  + Attack tree building
* Critical system
* Threat scanning

1. **Next work**: Alert correlation research

Each member must find the alert correlation’s survey and then share to all. Deadline to confirm result: 6h 5/9/2010

1. **Tasks**
   1. Build terminology system:

All used terminologies in project will be documented and explained to let all members get the same understanding about them.

* 1. Each member ~~plans a project timeline and then submits by using Google code project issue~~ must submit all issues/technical problems needed to be solved before implementation to his branch on Googlecode. Deadline to submit: 0h – 5/9/2010

1. **Group communication languages:**
   1. English

* Email
* Comment for all changing in SVN server.
* Minutes
  1. Vietnamese
* Others

1. **Group Rules**

* Each paper/document report must include keywords and these keywords will be ~~summary~~ summarized and ~~link~~ linked back to their corresponding paper for searching and filtering purposes.
* Every commits must have corresponding comment using group comment convention.
* Do not delete anything in documents. All uncorrected things will be saved and be good experience to avoid in future.
* All tasks must have deadline and all member must follow them.
* All issues will be concluded ~~after 1-2 days~~ after all members have ~~give~~ given opinions by using Google code server log.
* Penalty:
  + Late for comment / resources submitting: 20.000VND / 1 late hour from deadline.
  + Late for meeting: 5.000VND/a block 5 minutes late from meeting time.
  + Other mistakes: forget to add comment when commit, comment not follow group convention, commit to wrong folder …: 5.000VND/1 mistake.
* Rewards:
  + 10.000VND for the only member who can download and share paper/document that all group is finding.